## Overall
Task | Estimate (hours)
User Login | 3
Spotify Authentication | 2
Set up MongoDB database connection | 0.25
Create a User database model | 0.25
Write and use POST and GET requests for storing user info | 0.5
Google Maps | 3
Get the Google Maps API Key in GCP | 0.25
Implement the map | 1
Get the user's location | 1.25
Plot the user's location point on the map | 0.5
Get Music Choices | 3
Use the access token and user location to call spotify API to get list of music options | 1
Make the output of the API call look user-friendly | 1
Implement feature to allow users to save music to their own playlist | 1
More info on User's Tastes (if time permits) | 3
Add set of dropdowns to know more about user music tastes for better personalization | 1
Make UI improvements | 1
Experiment with Spotify API call with information from different dropdowns | 1
Project | 12

## Akhil
Task | Estimate (hours)
User Login | 3
Spotify Authentication | 2
Set up MongoDB database connection | 0.25
Create a User database model | 0.25
Write and use POST and GET requests for storing user info (need to make spotify API call to get user info) | 0.5

## Junho
Task | Estimate (hours)
Google Maps | 3
Get the Google Maps API Key in GCP | 0.25
Implement the map | 1
Get the user's location | 1.25
Plot the user's location point on the map | 0.5

## Annie
Task | Estimate (hours)
Get Music Choices | 3
Use the access token and user location to call spotify API to get list of music options | 1
Make the output of the API call look user-friendly | 1
Implement feature to allow users to save music to their own playlist | 1

## Jakob
Task | Estimate (hours)
More info on User's Tastes (if time permits) | 3
Add set of dropdowns to know more about user music tastes for better personalization | 1
Make UI improvements | 1
Experiment with Spotify API call with information from different dropdowns | 1